1085-14-5 (CO)

Copy No. ___ of ___ copies

Issued by ### Squadron

Anywhere, NS

15 March 1999  1900 AST

OPS ORDER NO. #1/99

### SQUADRON 50th ANNUAL CEREMONIAL REVIEW

Distribution List

References:		A.	A-CR-CCP-265/PC-001 Level Five Course Training Plan

B.	A-CR-CCP-269/PH-001 Level Four Course Training Plan

C.	A-CR-CCP-269/PT-001 Level Four Handbook

D.	A-PD-201-000/PT-001 Canadian Forces Manual of Drill 		and Ceremonial

1.	SITUATION

As stated in reference A, there is a requirement for the cadets and staff of subject squadron to participate in a Ceremonial Review.

2.	MISSION

XXX Royal Canadian Air Cadet Squadron will, on 29 May 1999, conduct a  Ceremonial Review (ACR) at Anyplace, Anywhere, NS. Personnel, 4 Officers, 3 Civilian Instructors, 45 cadets. (32 M, 13 F)

3.	EXECUTION

a.	General:

(1)	The dress for the staff and cadets is as follows:

(a)	Officers –  No.3A.

(b)	Cadets –  Full uniform with shirt and tie.

(c)	Civilian Instructors –  Equivalent to NO. 3A.

(2)	The Ceremonial Review will be broken down into three

distinctive phases:

(a)	Setup of the location where the Ceremonial Review will

take place.

(b)	The Ceremonial Review itself.

(c)	Tear down and clean up.

b.	Tasking:

(1)	Captain Bloggins, Commanding Officer (CO) will be responsible

for:

(a)	communication with Detachment, League, and Sponsors

on status of the ACR;

(b)	booking facilities for practice, preparation and the ACR;

(c)	ensuring the Reviewing Officer is properly briefed on

requirements and details of ACR; and

(d)	ordering and engraving of trophies and plaques;

(2)	Lt. Smart, Training Officer (Trg O) will be responsible for:

(a)	OPI Annual Ceremonial Review

(b)	coordination of all displays and demonstrations;

(c)	ensuring all training records are current and complete;

(d)	coordination of all parade practices and rehearsals using 				layouts attached in Annexes C, D and E;

(e)	preparation of News Releases one week prior and no

later than 1 week following the ACR; and

(f)	formulation and chairing of an ACR committee;

(3)	Lt. Busy, Administration Officer (Admin O) will be responsible 			for:

(a)	assume the role of Master of Ceremonies for the ACR;

(b)	preparation of ACR Information Sheet for CO’s 	signature;

(c)	preparation of CDT 790 Annual Report and submit to CO 				for signature;

(d)	completion of RCP1 and confirm support provided for 					ACR;

(e)	mailing written invitations for all guests;

(f)	development of a seating plan for invited guests;

(g)	preparation of the appropriate certificates of achievements;

(h)	preparation of letter describing the importance of the ACR

for parents; and

(j)	any other duties as assigned by the OPI.

(4)	2Lt. Doe, Supply Officer (Sup O)

(a)	procuring the list of supplies required as stated in

Annex B;

(b)	ensuring all cadets are in possession of properly fitting

and presentable uniform in co-ordination with the Cadet

Squadron Commander;

(c)	ensuring all requested equipment is returned;

(d)	formulation and chairing of an awards committee;

(e)	ensuring that the supply office is well maintained and in

order; and

(f)	any other duties as assigned by the OPI.

(5)	CI Willdo, Band Officer (Band O)

a.	ensuring band is prepared for ACR;

b.	preparation of Post-ACR banquet using seating

arrangement from Annex E;

c.	assume the role of usher in coordination with Trg O; and

d.	any other duties as assigned by the OPI.

(6)	CI Cando, Special Projects Officer (SPO)

(a)	setting up and tearing down of equipment and supplies

for spectators, parade square, displays and

demonstrations and reception;

(b)	preparation of reception in coordination with Sponsor.

(c)	assume the role of usher in coordination with Trg O; and

(d)	any other duties as assigned by the OPI.

(7)	CI Shutterbug, Photography Specialist

(a)	ensuring an adequate amount of pictures are taken of all

aspects of the ACR;

(b)	preparation of ACR program for submission to the CO;

(c)	distribution of approved program prior to ACR; and

(d)	any other duties as assigned by the OPI.

(8)	WO1 Cadence, Cadet Squadron Commander (Sqn Comd)

(a)	ensuring all cadets are possession of a properly fitting

and presentable uniform in coordination with the Sup O;

(b)	ensuring all cadets are prepared and enthused for ACR;

(c)	presentation to the RO;

(d)	coordination of leadership teams to assist the various

activity coordinators; and

(e)	any other duties as assigned by the OPI.

(9)	Sponsoring Body

a.	preparation of reception in coordination with SPO;

b.	provide the required meals as determined by the ACR

committee;

c.	ensuring that appropriate safety personnel are on hand

at all practices and the ACR;

d.	fund raising in support of donation to charitable

organization in the name of the RO; and

e.	any other duties as assigned by the CO/OPI.

c.	Coordinating Instructions:

(1)	Timings

Attached in Annex A

(2)	Parade Practices

The squadron will conduct the following practices:

a.	complete dress rehearsal on 26 May 1999 from 1900 –

2130 hrs AST; and

b.	full parade practice on 29 May 1999 from 0800 – 1100 				hrs AST.

(3)	ACR Committee

The ACR committee will consist of the CO, Trg O, Adm O,

Sup O and Sqn Comd. The Trg O will assume the

responsibility of chairing this committee which will conduct its

first meeting on 21 April 1999 from 1900 – 2100 hrs AST at

LHQ. All subsequent meetings will be determined at that time.

(4)	Awards Committee

The awards committee will consist of the CO, Trg O, Adm O,

Sup O, and Sqn Comd. The CO will assume the

responsibility of chairing this committee which will conduct its

first meeting on 22 April 1999 from 1900 – 2100 hrs AST at

LHQ.  All subsequent meetings will be determined at that time.

(5)	After Action Report

The ACR Committee will meet on 03 June 1999 from 1900 –

2100 hrs AST to provide feedback in support of the

development of an After Action Report.

4.	SERVICE & SUPPORT

a.	Transportation

The CO will ensure to request approval from the ACO’s Officer for

rental of a Panel Van for transporting materials and equipment.

b.	Equipment and Supplies

As required.

c.	Meals

As determined by the ACR committee in coordination with the CSG.

5.	COMMAND AND SIGNALS

a.	Command Appointments

(1)	The Ceremonial Review is conducted under the authority of 				The Nova Scotia Cadet Detachment and the Squadron 				Commanding Officer, Capt. J.D. Bloggins

(2)	OPI – Lt. Smart, Training Officer

2i/c – Lt. Busy

(3)	Chair of the ACR Committee – Training Officer

(4)	Chair of the Awards Committee – Commanding Officer

(5)	Master of Ceremonies – Administration Officer

J.D. Bloggins

Captain

Commanding Officer

XXX RCACS

# Annexes:	A. 	Time Appreciation

B. 	Equipment and Supply List (Pending)

C. 	Parade Square Layout

D. 	General Seating Arrangement

E. 	Seating Plan for Reviewing Party

F. 	Banquet Seating Arrangement

Distribution List

Action

CO

Trg O

Admin O

Sup O

Sqn Comd

Sponsoring Body

Information

Det Comd (NS)

ACO(Air)

League Rep

Sponsoring Body Chairperson

Annex A

To 1085-14-5 (CO)

# Scheduling

## PRE-ACR

ACR Committee Meeting at LHQ

Awards Committee Meeting at LHQ

Dress Rehearsal

Full Parade Practice

Full Parade Practice

Set-up (May be more than one time designated)

## ACR

Arrival of Cadets

Squadron Forms Up

Marching on of Flag Party

Arrival of Reviewing Officer

General Salute

Inspection

March Past

Presentation of Awards

Speeches

Advance and General Salute

Departure of Reviewing Officer

RO returns & Mobile Demonstrations

Training Displays

Reception

## POST-ACR

Tear down

Banquet

ACR Committee Meeting at LHQ (After Action Report)